## Common
Common to all ATLAS systems
Task | Type | Location | Period | Duration | Resp.
Longtime logging with Oracle DB | Consolidation |  |  |  | SH
Migration PVSS | Consolidation |  |  |  | SH
WEB pages for shifters | Consolidation |  |  |  | SH
Install sensors in experiment modules | Consolidation | SGX1+USA |  |  | PC
Relocate few flammable gas detection heads in SGX1 | Consolidation | SGX1 |  |  | TS (D.Hay)
Analysis Devices Verification/Calibration | Maintenance | SGX1 |  |  | LP

## TGC
ATLAS TGC
Task | Type | Location | Period | Duration | Resp.
Change purifier agents (1 rack) | Maintenance | SGX1 |  | 3d | AD
Check electrovalves in purifiers | Maintenance | SGX1 |  | 1h | AD
Check of pumps | Maintenance | SGX1 |  | 1d | AW
Control Mass Flow Controllers | Maintenance | SGX1 |  | 3d | VD
Cleaning of mechanical filters | Maintenance | SGX1 |  | 3d | FM
Safety Valves | Maintenance | SGX1+UX |  | 4d | FM
Bubblers (check and oil level) | Maintenance | UX |  | 2d | FM
Flow cells | Repair | UX |  | 4 w | RG
Remote power cycle Control Chassis (US) | Repair | USA |  |  | PC
Wiring Control Chassis (SG, US) | Repair | SGX1, USA |  |  | PC
Manometers (Tescom and Blondell) | Repair | USA |  |  | FM
Install Heating in parts of TGC distr. racks | Consolidation | UX |  | 2w | PC
Heat TGC pipes US - UX | Consolidation | USA-UX |  |  | ATLAS TC
Improve safety for TGC (input signals such as ventilation status) | Consolidation |  |  |  | ATLAS TC
TGC efficiency recovery | Consolidation | SGX1 |  | 2w | FM

## TRT
ATLAS TRT
Task | Type | Location | Period | Duration | Resp.
Recovery Rack (constr+install) | Consolidation | SGX1 |  |  | FM
Analysis Rack | Consolidation | SGX1 |  |  | FM
Shielding TRT Buffers | Consolidation | SGX1+USA |  |  | FM
Integration TRT CO2 cooling into ATLAS gas systems | Consolidation |  |  |  | SH
Add H-sensor in TRT ventilation | Consolidation | UX |  |  | LP | To be confirmed by H.Danielsson
Change purifier agents (1 rack) | Maintenance | SGX1 |  | 3d | AD
Check electrovalves in purifiers | Maintenance | SGX1 |  | 1h | AD
Check of pumps | Maintenance | USA |  | 1d | AW
Control Mass Flow Controllers | Maintenance | SGX1 |  | 3d | VD
Cleaning of mechanical filters | Maintenance | SGX1+USA |  | 3d | FM
Safety Valves | Maintenance | SGX1+UX |  | 4d | FM
Bubblers (check and oil level) | Maintenance | UX |  | 2d | FM
Modification of exhaust rack | Repair | SGX1 |  |  | FM | ?????
Remote power cycle Control Chassis (US) | Repair | USA |  |  | PC
Wiring Control Chassis (SG, US) | Repair | SGX1, USA |  |  | PC
Manometers (Tescom and Blondell) | Repair | USA |  |  | AD

## RPC
ATLAS RPC
Task | Type | Location | Period | Duration | Resp.
Purifier3 Rack | Consolidation | SGX1 |  |  | FM
Change purifier agents (1 rack) | Maintenance | SGX1 |  | 3d | AD
Check electrovalves in purifiers | Maintenance | SGX1 |  | 1h | AD
Check of pumps | Maintenance | USA |  | 1d | AW
Control Mass Flow Controllers | Maintenance | SGX1 |  | 3d | VD
Cleaning of mechanical filters | Maintenance | SGX1+USA |  | 3d | FM
Safety Valves | Maintenance | SGX1+UX |  | 4d | FM
Bubblers (check and oil level) | Maintenance | UX |  | 2d | FM
Modification of exhaust rack | Repair | SGX1 |  |  | FM | ?????
Remote power cycle Control Chassis (US) | Repair | USA |  |  | PC
Wiring Control Chassis (SG, US) | Repair | SGX1, USA |  |  | PC
Manometers (Tescom and Blondell) | Repair | USA |  |  | AD

## MDT
ATLAS MDT
Task | Type | Location | Period | Duration | Resp.
Analysis Rack | Consolidation | USA |  |  | FM
Change purifier agents (1 rack) | Maintenance | SGX1 |  | 3d | AD | LOW PRIORITY
Check electrovalves in purifiers | Maintenance | SGX1 |  | 1h | AD
Check of pumps | Maintenance | SGX1 |  | 1d | AW
Control Mass Flow Controllers | Maintenance | SGX1 |  | 3d | VD
Cleaning of mechanical filters | Maintenance | SGX1+USA |  | 3d | FM
Safety Valves | Maintenance | SGX1+UX |  | 4d | FM
Bubblers (check and oil level) | Maintenance | UX |  | 2d | FM
Modification of exhaust rack | Repair | SGX1 |  |  | FM | ?????
Remote power cycle Control Chassis (US) | Repair | USA |  |  | PC
Wiring Control Chassis (SG, US) | Repair | SGX1, USA |  |  | PC
Manometers (Tescom and Blondell) | Repair | USA |  |  | AD

## CSC
ATLAS CSC
Task | Type | Location | Period | Duration | Resp.
Control Mass Flow Controllers | Maintenance | SGX1 |  | 3d | VD
Cleaning of mechanical filters | Maintenance | SGX1+USA |  | 3d | FM
Safety Valves | Maintenance | SGX1+UX |  | 4d | FM
Bubblers (check and oil level) | Maintenance | UX |  | 2d | FM
Remote power cycle Control Chassis (US) | Repair | USA |  |  | PC
Wiring Control Chassis (SG, US) | Repair | SGX1, USA |  |  | PC
Verify Manometers (Tescom and Blondell) | Repair | USA |  |  | FM

## ID
ATLAS ID
Task | Type | Location | Period | Duration | Resp.
Safety Valves | Maintenance | SGX1+UX |  | 4d | FM
Bubblers (check and oil level) | Maintenance | UX |  | 2d | FM
Verify Manometers (Tescom and Blondell) | Repair | USA |  |  | FM
Add sensor to qualify type of gas (N2 system) | Consolidation | USA |  |  | LP | To be confirmed by H.Danielsson

## Sheet1
| Task | Location | Duration | Comment
Construction
1 | Purifier 3 RPC |  | 4 w | To decide when it should be done
2 | TRT Xe recuperation |  | 3 w | Delay is defined by purchase and aging validation of pump
Installation
3 | Shielding for TRT buffer tanks | SGX1, USA | 2 w
4 | TRT Xe recuperation | SGX1 | 2 w
5 | Analysis MDT | USA | 1 w
6 | Analysis TRT | USA | 1 w
7 | Install Heating in parts of TGC distr. racks | UX | 2 w
8 | Heat TGC pipes US - UX | US-UX | 3 w | To be evaluated
9 | Purifier 3 RPC | SGX1 | 1 w
10 | Relocate flammable gas detection heads in SGX1 | SGX1 | 1 w | Done by TS (D.Hay)
Controls
11 | Integration TRT CO2 cooling into ATLAS gas systems
12 | Longtime logging with Oracle DB
13 | Migration to PVSS
14 | WEB pages for shifters
15 | Improve safety for TGC (input signals such as ventilation status)
Hardware Upgrades
16 | TGC efficiency recovery | SGX1 | 2 w
17 | Install sensors in experiment modules | SGX1, USA | 1 w
M&O
18 | Check of pumps | SGX1, USA | 1 w | Dates can be adapted to ATLAS schedule
19 | Control Mass Flow Controllers | SGX1 | 2 w | "
20 | Cleaning of mechanical filters | SGX1 | 1 w | "
A list of components that need to be purchased for M&O is under preparation