## Common
Common to all CMS systems
Task | Type | Location | Period | Duration | Resp.
Longtime logging with Oracle DB | Consolidation |  |  |  | SH
Migration to PVSS | Consolidation |  |  |  | SH
WEB pages for shifters | Consolidation |  |  |  | SH
Install sensors in experiment modules | Consolidation | SGX5+USC |  |  | PC
Relocate few flammable gas detection heads in SGX5 | Consolidation | SGX5 |  |  | TS (D.Hay)
GC common analysis station | Consolidation | UGX |  |  | FM
Analysis Devices Verification/Calibration | Maintenance | SGX5 |  |  | LP

## RPC
ATLAS TGC
Task | Type | Location | Period | Duration | Resp.
Installation Purif 3 | Installation | SGX5 |  |  | AD
Analysis RPC | Installation | SGX5 |  |  | AD
Change purifier agents (2 racks) | Maintenance | SGX5 |  | 3d | AD
Check electrovalves in purifiers | Maintenance | SGX5 |  | 1h | AD
Check of pumps | Maintenance | USC |  | 1d | AW
Control Mass Flow Controllers | Maintenance | SGX5 |  | 3d | VD
Cleaning of mechanical filters | Maintenance | SGX5+UXC |  | 3d | AD
Safety Valves | Maintenance | SGX5+UXC |  | 4d | AD
Bubblers (check and oil level) | Maintenance | UX |  | 2d | AD
Modification of exhaust rack | Repair | SGX5 |  |  | AD
Flow cells | Repair | UX |  |  | RG
Remote power cycle Control Chassis (US) | Repair | USC |  |  | PC
Wiring Control Chassis (SG, US) | Repair | SGX5, USC |  |  | PC
Manometers (Tescom and Blondell) | Repair | USC |  |  | AD
RPC flowmeter check | Repair | UXC |  | 4w
RPC humidity sensors | Repair | UXC |  | 2w
Reinstallation of electrical boxes in -side racks in proper location | Repair | UXC |  | 1w | TS

## CSC
CMS CSC
Task | Type | Location | Period | Duration | Resp.
Analysis CSC | Installation | SGX5 |  |  | AD
Change purifier agents (1 rack) | Maintenance | SGX5 |  | 3d | AD
Check electrovalves in purifiers | Maintenance | SGX5 |  | 1h | AD
Check of pumps | Maintenance | USC |  | 1d | AW
Control Mass Flow Controllers | Maintenance | SGX5 |  | 3d | VD
Cleaning of mechanical filters | Maintenance | SGX5+UXC |  | 3d | AD
Safety Valves | Maintenance | SGX5+UXC |  | 4d | AD
Bubblers (check and oil level) | Maintenance | UX |  | 2d | AD
Modification of exhaust rack | Repair | SGX5 |  |  | AD
Remote power cycle Control Chassis (US) | Repair | USC |  |  | PC
Wiring Control Chassis (SG, US) | Repair | SGX5, USC |  |  | PC
Manometers (Tescom and Blondell) | Repair | USC |  |  | AD
Flowcells calibration (those with error>10%) | Repair | USC |  |  | RG
Reinstallation of electrical boxes in -side racks in proper location | Repair | UXC |  | 1w | TS

## DT
CMS DT
Task | Type | Location | Period | Duration | Resp.
Check electrovalves in purifiers | Maintenance | SGX5 |  | 1h | AD
Check of pumps | Maintenance | USC |  | 1d | AW
Control Mass Flow Controllers | Maintenance | SGX5 |  | 3d | VD
Cleaning of mechanical filters | Maintenance | SGX5+UXC |  | 3d | AD
Safety Valves | Maintenance | SGX5+UXC |  | 4d | AD
Bubblers (check and oil level) | Maintenance | UX |  | 2d | AD
Analysis Devices Verification/Calibration | Maintenance | USC |  | 3d | LP
Modification of exhaust rack | Repair | SGX5 |  |  | AD
Remote power cycle Control Chassis (US) | Repair | USC |  |  | PC
Wiring Control Chassis (SG, US) | Repair | SGX5, USC |  |  | PC
Manometers (Tescom and Blondell) | Repair | USC |  |  | AD
DT analysis system: final functionalities (analysis valves + control software) | Consolidation | UXC+UGX |  | 4w | RG, MC

## Sheet1
| Task | Location | Duration | Comment
Construction
1 | Purifier 3 RPC |  | 4 w | To decide when it should be done
Installation
2 | Analysis CSC | SGX5 | 1 w
3 | Analysis RPC | SGX5 | 1 w
4 | Purifier 3 RPC | SGX5 | 1 w
5 | Relocate few flammable gas detection heads in SGX5 | SGX5 | 1 w | Done by TS (D.Hay)
6 | GC common analysis station | UGX | 3 w
7 | TOTEM - end (completion) | UXC+UGX | 3 w | Work for Totem has to be specified and agreed in detail. Procurement of parts and heavy piping work in cavern are still needed.
8 | TOTEM +end | UXC+UGX | 4 w
Commissioning
9 | TOTEM | UXC | 2 w | To be done after installation is completed (see comment above)
10 | DT analysis system: final functionalities (analysis valves + control software) | UXC+UGX | 4 w
Controls
11 | Longtime logging with Oracle DB
12 | Migration to PVSS
13 | WEB pages for shifters
Hardware Upgrades
14 | Install sensors in experiment modules | SGX5+USC | 1 w
15 | RPC flowmeter check | UXC | 4 w
16 | RPC humidity sensors | UXC | 2 w
M&O
17 | Check of pumps | SGX5+USC | 1 w | Dates can be adapted to CMS schedule
18 | Control Mass Flow Controllers | SGX5 | 2 w | "
19 | Cleaning of mechanical filters | SGX5+UXC | 1 w | "
20 | A list of components that need to be purchased for M&O is under preparation