## Common
Common to all LHCb systems
Task | Type | Location | Period | Duration | Resp.
Longtime logging with Oracle DB | Consolidation |  |  |  | SH
Migration to PVSS | Consolidation |  |  |  | SH
WEB pages for shifters | Consolidation |  |  |  | SH
Install sensors in experiment modules | Consolidation | SGX8+UXA |  |  | PC
Relocate few flammable gas detection heads in SGX5 | Consolidation | SGX8 |  |  | TS (D.Hay)
Analysis Devices Verification/Calibration | Maintenance | SGX8 |  |  | LP

## MUON
LHCb MUON
Task | Type | Location | Period | Duration | Resp.
Change purifier agents (1 rack) | Maintenance | SGX8 |  | 3d | AD
Check electrovalves in purifiers | Maintenance | SGX8 |  | 1h | AD
Check of pumps | Maintenance | UXA |  | 1d | AW
Control Mass Flow Controllers | Maintenance | SGX8 |  | 3d | VD
Cleaning of mechanical filters | Maintenance | SGX8+UXB |  | 3d | FM
Safety Valves | Maintenance | SGX8+UXB |  | 4d | AD
Bubblers (check and oil level) | Maintenance | UXB |  | 2d | AD
Modification of exhaust rack | Repair | SGX8 |  |  | FM
Remote power cycle Control Chassis (US) | Repair | USC |  |  | PC
Wiring Control Chassis (SG, US) | Repair | SGX8, USC |  |  | PC
Verfify Manometers (Tescom and Blondell) | Repair | Everywhere |  |  | SP

## OT
LHCb OT
Task | Type | Location | Period | Duration | Resp.
Analysis rack | Installation | UXA |  |  | AD
Control Mass Flow Controllers | Maintenance | SGX8 |  | 3d | VD
Cleaning of mechanical filters | Maintenance | SGX8+UXB |  | 3d | AD
Safety Valves | Maintenance | SGX8+UXB |  | 4d | AD
Bubblers (check and oil level) | Maintenance | UX |  | 2d | AD
Modification of exhaust rack | Repair | SGX8 |  |  | AD | LOW PRIORITY!
Remote power cycle Control Chassis (US) | Repair | UXA |  |  | PC
Wiring Control Chassis (SG, US) | Repair | SGX8, UXA |  |  | PC
Manometers (Tescom and Blondell) | Repair | UXA |  |  | AD

## RICH1
LHCb RICH1
Task | Type | Location | Period | Duration | Resp.
Control Mass Flow Controllers | Maintenance | SGX8 |  | 3d | VD
Cleaning of mechanical filters | Maintenance | SGX8+UXB |  | 3d | AD
Safety Valves | Maintenance | SGX8+UXB |  | 4d | AD
Bubblers (check and oil level) | Maintenance | UX |  | 2d | AD
Modification of exhaust rack | Repair | SGX8 |  |  | AD
Remote power cycle Control Chassis (US) | Repair | UXA |  |  | PC
Wiring Control Chassis (SG, US) | Repair | SGX8, UXA |  |  | PC
Manometers (Tescom and Blondell) | Repair | UXA |  |  | AD

## RICH2
LHCb RICH2
Task | Type | Location | Period | Duration | Resp.
Control Mass Flow Controllers | Maintenance | SGX8 |  | 3d | VD
Cleaning of mechanical filters | Maintenance | SGX8+UXB |  | 3d | AD
Safety Valves | Maintenance | SGX8+UXB |  | 4d | AD
Bubblers (check and oil level) | Maintenance | UX |  | 2d | AD
Modification of exhaust rack | Repair | SGX8 |  |  | AD
Remote power cycle Control Chassis (US) | Repair | UXA |  |  | PC
Wiring Control Chassis (SG, US) | Repair | SGX8, UXA |  |  | PC
Manometers (Tescom and Blondell) | Repair | UXA |  |  | AD